## Sheet1
PAGES | SUB Menu level 1 | SUB Menu level 2 | Sub Page 1 | Sub page 2 | Estimation(Day) | Total Part Estimation
Landing Page |  |  |  |  | 16
Login |  |  |  |  | 0.5
Dashboard | File
Edit
System
| Mission Planning | Mission Template | root | - | 2 | 6
|  |  | Create Mission |  | 1
|  |  | Edit Mission |  | 1
|  |  | Delete Mission |  | 1
|  |  | View Details |  | 1
|  | Prepared Mission | root |  | 2 | 7
|  |  | Create Prepared Mission |  | 1
|  |  | Edit Prepared Mission |  | 1
|  |  | Delete Prepared Mission |  | 1
|  |  | View Prepared Mission |  | 2
|  | Scheduled Mission | root |  | 2 | 7
|  |  | Schedule Mission |  | 1
|  |  | Reschedule Mission |  | 1
|  |  | Delete Mission |  | 1
|  |  | Refresh |  | 1
|  |  | Send To Queue |  | 1
|  | On Line Command | root |  | 3 | 3
| Pass Time | Show Pass Time | root |  | 2 | 2
| GS | GS status | root |  | 3 | 3
| Monitoring | MTO | root |  | 2 | 2
|  | Telemetry | root | parameter per page(EPS,TCS,..) | Depends on project minimum 3 | up to 3
|  | ACS Telemetry | root | parameter per page(EPS,TCS,..) | Depends on project minimum 3 | up to 3
|  | New Telemetry | root | parameter per page(EPS,TCS,..) | Depends on project minimum 3 | up to 3
|  | Updatable Param | root | parameter per page(EPS,TCS,..) | Depends on project minimum 3 | up to 3
|  | Telemetry Summary | root | parameter per page(EPS,TCS,..) | Depends on project minimum 3 | up to 3
|  | Event Reporting | root | parameter per page(EPS,TCS,..) | Depends on project minimum 3 | up to 3
|  | Telecomand Status | online status |  | 2
|  |  | mission status |  | 2
|  | GS status | root |  | 2
|  | TC Verification | root |  | 2
|  | ALL Telemetry | root |  | 2
|  | Hk Graph |  |  | 2
|  | Health Telemetry |  |  | 2
| Control Panel | PUS Service | root |  | 2
|  |  | Add Pus Service |  | 1
|  |  | Edit Pus Service |  | 1
|  |  | Delete Pus Service |  | 1
|  |  | Add Telecommand |  | 1
|  |  | Edit Telecommand |  | 1
|  |  | Delete Telecommand |  | 1
|  |  | Add Parameter |  | 1
|  |  | Edit Parameter |  | 1
|  |  | Delete Parameter |  | 1
|  | SID | root |  | 2
|  | Define New Sid | root |  | 2
|  | Definition Telecommand | root |  | 2
|  |  | Add Telecommand |  | 1
|  |  | Edit Telecommand |  | 1
|  |  | Delete Telecommand |  | 1
|  |  | Add Parameter |  | 1
|  |  | Edit Parameter |  | 1
|  |  | Delete Parameter |  | 1
|  | Manage Account | root |  | 2
|  | Manage Role | root |  | 2
|  | Manage Access Control | root |  | 2
|  | Parameter Management | root |  | 2
|  | Event Description | s |  | 2
|  | Define Object |  |  | 1
|  | Define Mode |  |  | 1
|  | Define SubMode |  |  | 1
|  | Parameter Type | PT Format |  | 1
|  |  | PT Type |  | 1